# EcoHealth Analytics Platform — Project Proposal

Objective: Develop an analytics platform that correlates Egypt's air quality metrics (PM2.5, PM10, NO2) with public health outcomes and economic costs, delivering a data-driven report, predictive insights, AI-powered scenario simulations, and an interactive dashboard to support environmental and health decision-making.

Description: Egypt’s industrial and urban centers face seasonal spikes in air pollution, but no integrated view links pollutant levels to health outcomes (respiratory illness, hospitalizations) and economic burden (healthcare costs, lost productivity/DALYs). This project closes that gap by delivering a unified dataset, an in-depth analytical report, predictive modeling, AI-driven insights, and an interactive Power BI dashboard visualizing pollution, health, and economic trends across Egyptian governorates.

Tools & Design:

- Interactive multi-page Power BI dashboard with geospatial heatmaps, KPI cards, and dynamic filter controls

- Python (Pandas) ETL pipeline merging environmental and health datasets by Year/Governorate

- Statistical correlation analysis in SQL and Python (Seaborn/Matplotlib)

- Machine learning models (Regression, Random Forest, Neural Networks) for predictive health and economic outcomes

- AI sector capabilities: NLP for health reports, computer vision for satellite imagery, optimization models for policy scenarios, AI-powered forecasting for pollution spikes

- Technologies: Python (Pandas, NumPy, Scikit-learn, TensorFlow, Matplotlib, Seaborn); SQL; PostgreSQL/MySQL; Power BI/Tableau; GitHub

- Data sources: OpenAQ API, NASA POWER, State of Global Air (SGA)/WHO/GBD Tool

Team Members & Responsibilities

- Data Analyst – Data cleaning, statistical & correlation analysis, Power BI dashboard design, final report writing

- Machine Learning Engineer – Build predictive models linking pollution levels to health outcomes and economic costs; validate and optimize models; integrate predictions into dashboard

- AI Specialist – Develop advanced AI modules (NLP, computer vision, optimization models, forecasting); generate scenario simulations and policy recommendations; integrate AI outputs into dashboard

# Week 1: Data Acquisition – Environmental & Health Data Collection

- Identify Egypt-specific data sources (OpenAQ, NASA POWER, SGA/WHO/GBD)

- Set up API access and authentication for OpenAQ and NASA POWER

- Export historical health records from State of Global Air

- Fetch pollutant data (PM2.5, PM10, NO2) by governorate and timestamp

- Fetch meteorological data (temperature, humidity, wind speed, solar radiation)

- Document data dictionary and source metadata

# Deliverables:

- Raw air quality dataset (CSV)

- Raw health outcomes dataset (CSV)

- Raw meteorological dataset (CSV)

- Data source documentation

# Week 2: Data Cleaning, Integration & Exploratory Analysis

- Handle missing values and standardize timestamps in Python (Pandas)

- Merge environmental and health datasets on Year/Governorate

- Load unified dataset into PostgreSQL/MySQL

- Perform statistical correlation analysis (SQL, Python)

- Visualize pollution vs. health trends (Seaborn/Matplotlib)

- Identify primary pollution drivers per governorate

# Deliverables:

- Unified, cleaned dataset (CSV/SQL)

- EDA correlation report

- Initial visualizations of pollution-health trends

- List of key pollution drivers identified

# Week 3: In-Depth Analysis, Predictive Modeling & AI Development

# Deepen correlation analysis across pollutants, health outcomes, and economic indicators

# Quantify estimated economic costs and DALYs from pollution exposure

# Segment analysis by governorate and season

# Develop predictive models (ML) to forecast health outcomes and economic costs

# AI sector tasks:

# NLP analysis of health reports and public datasets

# Computer vision for satellite imagery to detect pollution sources

# Optimization models for policy scenario testing

# AI forecasting of pollution spikes using meteorological data

# Validate models with historical datasets

# Draft written findings and key insights

# Peer review analysis and figures

# Deliverables:

# Draft analytical report

# Governorate/season-level insight summary

# Predictive model outputs and validation metrics

# AI-driven scenario simulations and forecasts

# Final set of charts and figures

# Reviewed findings

# Week 4: Dashboard Development & Final Reporting

# Design multi-page Power BI dashboard layout

# Build geospatial heatmaps of high-risk governorates

# Add KPI cards and dynamic filter controls

# Integrate predictive model outputs and AI scenario simulations into dashboard

# Align dashboard visuals with report findings

# Finalize written report with recommendations

# Conduct final review, testing, and presentation prep

# Deliverables:

# Interactive Power BI dashboard (multi-page, including predictive insights and AI-driven scenarios)

# Final analytical report with recommendations

# Presentation deck summarizing findings

# Project documentation on GitHub